## Pipeline
# | Client | Lead Topic | BD SPOC | FP LEAD | Received | RFP | Category | Status | QAF | Submission Deadline | Vendor needed? | Actions done | Next Step | Deadline for Next Step | Comments | MSR
5 | Al Haram - Al Madinah | Operation Center- VMS for Operation & Command Center | Mohammad Abdulkarim​​​​ Almuhesseny | GHH | 2025-03-24 | No | Strategic bet | Lead | N/A |  | Yes | -DT submitted preliminary costing -Assessed in house capability (not available) -NDA signed with ISS | -Re-initiate contact with ISS once done with P1 opportunities | 2025-06-30
1 | RCRC | CCTV network and traffic dashboard (PMD) | Muath Fahad Almohawes |  | 2025-04-23 | No | Hot deals | Opp-OnHold | N/A |  |  | -Mapped capability readiness based on our understanding (preliminary assessment) | -Secure full scope of work
2 | RCRC | Yield to pedestrian fine enforcement (SD) | Muath Fahad Almohawes |  | 2025-04-23 | No | Strategic bet | Opp-OnHold | N/A |  |  | -Mapped capability readiness based on our understanding (preliminary assessment) | -Secure full scope of work
3 | RCRC | Enforcement of ramp meter signals (SD) | Muath Fahad Almohawes |  | 2025-04-23 | No | Tactical distraction | Opp-OnHold | N/A |  |  | -Mapped capability readiness based on our understanding (preliminary assessment) | -Secure full scope of work
4 | RCRC | 3D wayfinding inside metro station (AI) | Muath Fahad Almohawes |  | 2025-04-23 | No | Dead weight | Opp-OnHold | N/A |  |  | -Mapped capability readiness based on our understanding (preliminary assessment) | -Secure full scope of work
6 | The Ministry of Transport and Logistics Services | Highway Inspection & Monitoring Operations | Faisal Bin Haddab | ELW | 2025-04-18 | No | Hot deals | Opp-OnHold | 100% |  |  | -Drafted QAF | -Ahmed Alkhaldi to assign a team for exploration -BD to schedule a meeting with the client | 2025-06-30 | This request is a study
7 | Aseer Municipality | Smart Parking | Muath Fahad Almohawes | GHH | 2025-03-26 | No | Strategic bet | Lead | N/A |  | Yes | -MOU signed at LEAP -Shared Survey -Conducted Site Visit - NDA signed with Flowbird - Shared Technical Solution | - Pending BD to schedule a meeting with Aseer -Pending BD comments on Technical Solution | 2025-07-06 |  | 5
8 | Ministry of Tourism | Hotel Violations | Faisal Bin Haddab | ELW | 2025-04-17 | No | Dead weight | Lead |  |  |  | -Attended meeting with client to gather requirements -BD Team to share MOM and detailed requirements - Shared all requirements with AIAT -Received verbal communication that Hikvision will provide a free poc and can finalize it in 1 week -Conducted SITE visit -Receied clearance letter from MOT to initiate camera installation -Identified execution site | - AI team to set a date for POC installation with Hikvision | 2025-07-03 | No actions on us now on hold and bd to confirm if we need to do a poc or not (as per our conversation with Faisal on 23/06/2025)
9 | SAL Saudi Logistics Services Company SJSC | AI-based logistics solution | Abdulaziz Alshedayed | LAH | 2025-04-28 | No | Dead weight | Failed |  |  |  | - Conducted a site visit on the 22nd of May - Received site visit report and insights - Received CRD from BD - Sent an email to Dr. Salem & Aldossary for capability check (26/06/2025) - Reminder Sent (30/06/2025) - AI Team confirmed that we currently do not have the required capabilities, shared information with BD (03/07/25) | - BD to obtain management approval - Confirm with BD that we can kill it
10 | Saudi Aramco | LLM (Large Language Model) Solution | Danah Alothman | GHH | 2025-05-08 | No | Dead weight | Failed | N/A |  |  | -Checked with Dr. On LLM readiness (could be ready in 12month) | -Gather meeting report and next steps from Danah |  | Rawan recommended not to proceed
11 | MOJ | LLM (Large Language Model) Solution | Muath Fahad Almohawes | ELW | 2025-05-01 | No | Dead weight | Failed |  |  |  | -Checked with Dr. On LLM readiness | -BD to check with MOJ on the scope and NDA
12 | RIPC | Licensing Platform Development | Abdullah Almehrej | ELW | 2025-05-13 | Yes | Strategic bet | Opp-Win | 100% | 2025-06-04 |  | - Drafted QAF - Drafted RFI - Shared Costing - Shared Technical Write-Up - Addressed all comments - Proposal Submitted | - BD to provide outcome of proposal submission | 2025-06-23 |  | 5
13 | Civil Defense | Fire & Safety IOT [N/A] | Faisal Bin Haddab | GHH | 2025-02-01 | Yes | Dead weight | POC | N/A |  | Yes | -In process of finalizing NDA | -Initiate installation in KAFD - Pending NDA between KAFD and Honeywell - AIAT allocate a SPOC for the project exploration
14 | Jeddah Municipality | Construction Waste & Visual Pollution [N/A] | Abdulrahman Almarshad |  | N/A | No | Strategic bet | Opp-OnHold | N/A |  |  | -Initiated exploration workshop | -BD to accelerate NDA sign-off
15 | Riyadh Municipality | Buildings Compliance & Ads on Vehicles [N/A] | Saleh Alfuzan | RAE | N/A | No | Tactical distraction | Opp-OnHold | N/A |  |  |  | -RAE to discuss with Hamid + Rabih to re-ignite the opportunitiy | 2025-05-25
16 | MOMAH | Construction Waste & Visual Pollution [N/A] | Omar Hatem S Aldossary | RAE | N/A | No | Strategic bet | Opp-OnHold | N/A |  |  | -Initiated opportunity discovery -Delivered high-level architecture -Addressed all DGA feedback | -BD to update the shared revenue model status -Approve DevOps workflow for DGA technical proposal -Conduct strategic discussion with BD, to engage with NHC (Balady Company) |  | check update with Rauf
17 | RIPC | Smart City [Field Tracking Solution] | N/A | ELW | 2025-01-29 | No | Hot deals | Opp-OnHold | N/A |  |  | -Delivered comprehensive Field Tracking Solution | follow up with Omar the latest then with BD if need be |  | -On hold from BD untill further notice | 1
18 | MOI | Amn Platform Development | Khaled Salem Balobaid | ELW | 2025-04-06 | Yes | Strategic bet | Opp-Submitted | 100% |  |  | -Drafted QAF -Shared RFI -Shared costing -Shared technical write-up -Email sent to BD requesting overview/update (30/06/2025) -Proposal submitted (30/06/2025) | - BD to provide overview on status |  |  | 4
19 | Remat Al Riyadh | Off-street parking | Danah Alothman |  | 2025-02-24 | Yes | Strategic bet | Line cancelled | 80% |  |  | -RFI shared -High Level Solution shared | -FP to find vendor for smart parking -Client to share RFP |  |  | 4
20 | Saudi Aramco | Urban Eye: Visual Pollution Project | Abdulaziz Alshedayed | ELW | 2025-02-01 | No | Hot deals | POC | N/A |  |  | - Aligned with DT team on environments readiness and costing - Shared insights from site visit - Ahmad alkhaldi to provide poc costing structure with DT putting in mind duration is 1 month - DT shared technical write-up and costing - Abdulaziz Almuhsen shared POC - POC Report shared with Aramco | - Pending client to provide feedback and update on next steps |  | There is another thread between BD and AI, we're not included in it, they are aligning and pending client approval that they need poc to share it
21 | KFCA | Urban Mobility Solutions [AI-Driven Traffic Management] | Abdulaziz Alkhwatiem | ELW | 2025-03-09 | Yes | Strategic bet | Opportunity | 80% |  |  | - Provided list of required qualification documents - QAF scored 80% - Received RFP (01/07/2025) | - Share Questions (July 8) - High Level Solution Design (July 17) - Estimated Cost (July 20) - Technical Proposal (July 31) | 2008-07-08 |  | 3
22 | Al Haram - Al Madinah | Holy Mosque Courtyard | Mohammad Abdulkarim​​​​ Almuhesseny | LAH | 2025-04-14 | No | Dead weight | POC | N/A |  |  | - POC document/solution was provided (by AI Team) - Cost estimate was provided - Reminders sent to BD - BD agreed on 12 month timeline | - Pending direction from BD to proceed with AI team (Abdulaziz Almohsen) |  | Sent reminder 2(19/06/2025) to BD SPOC to provide answer regarding 12 months execution Reminder 3 sent (08/07/25) | 5
23 | National Observatory for Quality of Life | National Observatory for Quality of Life Program | Abdulaziz Alshedayed | GHH | 2025-04-16 | Yes | Dead weight | Opp-Lost | 94.5% |  |  | -LLM readiness confirmed -Shared QAF -Shared RFI -Shared costing -Shared technical write-up | - Pending Previous Project done by Tahakom | 2025-05-22 | BD Team did not submit it | 4
24 | Saudi Aramco | Road Safety | Danah Alothman | LAH | 2025-02-24 | No | Hot deals | Opp-Lost | N/A |  |  | - PMD team did a site visit - PMD team drafted solution design - Solution Design was shared - Costing was shared | -Finalize proposal -Submit proposal -Secure approvls from senior management |  | Management decided not to proceed with a free poc
25 | Remat Al Riyadh | Smart City [Smart Micromobility] | Khaled Salem Balobaid | ELW | 2025-02-25 | Yes | Strategic bet | Opp-Lost | N/A |  |  | -QAF was prepared -Developed Technical Proposal -BD cancelled opportunity |  |  |  | 2
26 | GCA | Smart City [Smart Parking] | Abdullah Almehrej | GHH | 2025-02-13 | Yes | Strategic bet | Opp-Lost | 89% |  |  | -QAF was prepared -Developed Technical Write-Up | -Pending action/feedback from Abdullah Almehrej -killed sinve no response -BD to review budget on SD scope |  | No response from follow up after 3 trials | 2
27 | Great Amman Municipality | Smart City [N/A] | N/A |  | N/A | No | Strategic bet | Opp-Lost | N/A |  |  | -BD team changed technical proposal approach |  |  | BD team missed submission deadline
28 | Aseer Municipality | Visual pollution | N/A |  | N/A | No | Strategic bet | Opp-Lost | N/A |  |  | -MOU signed at LEAP event with activation initiated. -Drafted a comprehensive solution aligned with Asir Municipality’s requirements. |  |  | Current interest is on smart parking, client is not interested in visual pollution for the time being
29 | Saudi Aramco | Drone Management | Muath Fahad Almohawes |  | 2025-03-23 | No | Dead weight | Failed | 50% |  |  | -QAF scored below 50% (AIAT team doesn't have the Drone capability) -Shared a set of questions to know the size of the opportunity | - Client to respond to RFI shared to know the size of the opportunity. - Build up drone capability if the opportunity persists or find a suitable vendor
30 | MOI | مدارس تعليم القيادة[N/A] | N/A |  | N/A | No | Dead weight | Failed | N/A |  |  | - Analyzed RFP (not in scope)
31 | SAR | Railway Operations Suite[N/A] | Abdulaziz Alkhwatiem |  | 2024-12-29 | No | Dead weight | Failed | N/A |  |  | - MOU signed at LEAP event with activation initiated
32 | MOF | Oman Business Platform [Digital Platform] | Muath Fahad Almohawes |  | 2025-02-05 | Yes | Dead weight | Failed | 59.5% |  |  | - Drafted QAF |  |  |  | 1
33 | Saudi Aramco | Smart Solution For Telecom Rooms [N/A] | N/A |  | N/A | No | Tactical distraction | Opp-Lost | N/A |  |  | - Conducted workshop with BD to align scope requirement - Killed too small and not relevant
34 | Ministry of National Guard Development | Program Communication Plan | Abdulaziz Mohammed​​​​ Alshedayed |  | 2025-04-09 | yes | Dead weight | Failed | N/A |  |  | - Analyzed RFP (not in scope)
35 | DGA | Establishing Proactive Government | Khaled Salem Balobaid |  | 2025-03-11 | yes | Dead weight | Failed | 20% |  |  | - Drafted QAF
36 | DGA | Creative Content Management | Khaled Salem Balobaid |  | 2025-03-11 | yes | Dead weight | Failed | 25% |  |  | - Drafted QAF
37 | Trust Fund Minors And Their Counterparts | Cybersecurity Services | Muath Fahad Almohawes |  | 2025-03-13 | yes | Dead weight | Failed | 30%
38 | Aseer Municipality | Construction Waste | N/A |  | N/A | No | Strategic bet | Opp-Lost | N/A |  |  | - Aseer focus is on smart parking now killed
39 | Haramen | Digital Platform [Digital Procurement Services] | Mohammed Abdulrahman​​​​ Alyabis |  | 2025-03-05 | No | Dead weight | Failed | N/A |  |  | -Reviewed RFI documentation -Submitted clarification questions |  |  | The client is currently working on internal procedures related to this opportunity. Once they are ready to move forward, they will reach out to us, and we will make sure to keep you updated accordingly. | 3
40 | DGA | AI-Driven Service Enhancement [Delivering MVPs] | Khaled Salem Balobaid |  | 2025-03-11 | yes | Tactical distraction | Failed | 73% |  |  | - Drafted QAF - Shared Questionnaire |  |  |  | 3
41 | DGA | Innovation Hub Operations | Khaled Salem Balobaid |  | 2025-03-11 | yes | Dead weight | Failed | 62% |  |  | - Drafted QAF - Shared Questionnaire |  |  |  | 3
42 | DGA | Innovation Hub Education | Khaled Salem Balobaid |  | 2025-03-11 | yes | Dead weight | Failed | 87% |  |  | -Drafted QAF |  |  |  | 3
43 | RIPC | Business Continuity / DR | Muath Fahad Almohawes | LAH | 2025-05-15 | Yes | Hot deals | Opp-Win | 100% | 2025-06-08 |  | - Submit QAF (19May) - Submit RFI (19May) - Shared Technical Write-up + Cost with Omar & Faisal for review (May 29) - Shared Technical Write-up + Costing shared with BD (Muath) - June 2 - Conducted meeting with RIPC to discuss high-level design - Adressed all comments + updated HLD - Proposal was submitted (6 July) |  |  |  | 5
44 | COOP/Tawuniya driving | Smart Parking solution | Rawan Sultan Alsaadoun | ELW | 2025-05-18 | No | Strategic bet | Opp-OnHold | N/A | [5 empty] | no budget asking about the capability
45 | RIPC | Development of Monitoring Platform | Ahmed Mohamad A Alraba | ELW | 2025-05-19 | Yes | Strategic bet | Opp-Win | 100% | 2025-06-29 |  | - Shared QAF - Shared RFI - Shared Costing - Shared Technical Write-Up - Addressed all comments | - BD to provide stauts |  |  | 5
46 | MOI-Transformation Program | Multiple opportunities received for evaluation | Abdulaziz Alshedayed | GHH |  | No |  | Lead |  |  |  | - Shared the excel with BD | -Follow up with BD on next steps | 2025-07-07
47 | RIPC | Business Intelligence Platform Development and Data Management Tools | Khaled Salem Balobaid | LAH | 2025-05-19 | Yes | Strategic bet | Opp-Submitted | 100% | 2025-06-15 |  | - Submit QAF - Submit RFI - Technical Write-up + Costing shared with BD (khalid) - June 2 - Addressed all comments - Conducted meeting with RIPC answering all RFI questions - Proposal was submitted (6 July) |  |  | منافسة تطوير منصة ذكاء وتحليل الأعمال وأدوات إدارة البيانات | 5
48 | Amanat Alsharqiyah | Smart Parking | N/A | ELW | 2025-02-26 | No | Strategic bet | Lead |  |  |  | - Drafted Solution | - Follow up with business to understand the next steps |  | Aseel Almoosa is the Account Manager, reached out to her on June 16 to get an update, client still asessing | 2
49 | RIPC | Operation and maintenance of Security Systems | Rawan Sultan Alsaadoun | ELW | 2025-05-21 | Yes | Strategic bet | Failed |  | 2025-06-03 |  | - Opportunity Killed by BD
50 | SWA | AI platform | Rawan Sultan Alsaadoun | GHH | 2025-05-25 | Yes | Tactical distraction | Failed | 45%
51 | National Center for Privatization & PPP | Driving School | Abdullah Almehrej | ELW | 2025-05-21 |  | Strategic bet | Opportunity |  | 2025-09-09 |  | -BD team conducted initial understanding meeting with the client -BD team shared RFP - Attended kickoff meeting with EDC - Formulated a technical team which attended the 1 week war room with EDC - Shared list of questions | - Share cost (July 31) - Share Write-Up (10 August) - AIAT to finalize solutions (HR, payment and finance module (SAP)) - Mahmoud Hassan - AIAT to finalize solutions (Integration approach with government portal for identity verification (Nafath) - AIAT) - Mahmoud Hassan |  | Bid submission is 9 september as per RFP volume 1
52 | Remat Al Riyadh | Surface Public Parking Project – Phase One | Danah Alothman | LAH | 2025-06-03 | Yes | Strategic bet | Opp-OnHold | 87% | 2025-07-28 |  | - Shared QAF - Shared Opportunity Card | - Questionnaire (June 26) - Technical Write-up + Cost (July 6) | 2025-06-26 | financially not good enough
53 | Remat Al Riyadh | Surface Public Parking Project – Phase Two | Danah Alothman | LAH | 2025-06-03 | Yes | Strategic bet | Opp-OnHold | 87% | 2025-07-28 |  | - Shared QAF - Shared Opportunity Card | - Questionnaire (June 26) - Technical Write-up + Cost (July 6) | 2025-06-26 | financially not good enough
54 | Remat Al Riyadh | Multistorey Parking Project – Al Sahafa District | Abdullah Almehrej | ELW | 2025-06-03 | yes | Strategic bet | Opportunity | 90.8% | 2025-08-01 |  | - Drafted Opportunity Card - Shared QAF - Shared Questionnaire (July 9) | - Technical Write-up + Cost (Aug 1) | 2001-08-01
55 | State Properties General Authority - SPGA | حماية عقارات الدولة من التعديات - AI | Rawan Sultan Alsaadoun | GHH | 2025-06-03 | No | Dead weight | Failed |  |  |  | - Analyzed RFP (No capability) - Opportunity dropped with Abu Hamad
56 | MWAN | Construction Waste Solution | Abdulaziz Alshedayed | LAH | 2025-06-24 | No | Hot deals | Lead |  |  |  | - Sent an email to Dr. Salem & Aldossary for capability check (30/06/2025) - Shared AI's confirmation regarding available capabilities with BD - Sent follow up on lead status (8/7/25) | - Abdulaziz Ali Almohsen to provide availibility to set up a meeting with the client to gather requirements
57 | Riyadh Airport | Visual Pollution | Abdulaziz Alshedayed | LAH | 2025-06-24 | No | Hot deals | POC |  |  |  | - Sent an email to Dr. Salem & Aldossary for capability check (26/06/2025) - Shared AI's confirmation regarding available capabilities with BD - Sent follow up on lead status (8/7/25) - AI Suggested POC - Requested from AI Team information to proceed with POC | - Pending PMD to provide BD with costing
58 | Civil Defense | List of 26 opportunities | Mohammad Abdullah M Alwateed | GHH | 2025-06-26 | No | Hot deals | Lead |  |  |  | - Attended meeting with Civil Defense to align on the priorities - Received direction from Alkhaldi to hold a bit until we get updates from VP | -Prioritize opportunities and secure approval from management on next steps - Alkhaldi to provide update on discussion with VP |  | To be discussed with AZZ
59 | Ministry of Tourism | Hotel Evaluation Criteria | Muath Fahad Almohawes | LAH | 2025-07-14 | No | Tactical distraction | Lead |  |  |  | - BD Requested capability confirmation - Couldnt answer them. Asked for more info or RFP | - BD to provide more details on requirements
60 | GSTC | Performance Management Solution | Rawan Sultan Alsaadoun | LAH | 2025-07-07 | No | Tactical distraction | Lead |  |  |  | - BD Requested capability confirmation - Couldnt answer them. Asked for more info or RFP | - BD to provide more details on requirements
61 | Remat Al Riyadh | Surface Public Parking Project – Murabah Street | Faisal Bin Haddab | LAH | 2025-07-14 | Yes | Strategic bet | Opportunity | 87% |  |  | - Assessing solution with KTC/Dezigna | - Share Technical Write-Up - Share costing
62 | Remat Al Riyadh | Mechanical Parking - Lot 4 | Abdulaziz Alshedayed | LAH | 2025-07-14 | Yes | Strategic bet | Opportunity | 100% |  |  | - Assessing solution with KTC/Dezigna | - Share Technical Write-Up - Share costing
63 | Remat Al Riyadh | Multistorey parking - Lot 5 | Khaled Salem Balobaid | ELW | 2025-07-14 | Yes | Strategic bet | Opportunity | 90.8% |  |  | - Assessing solution with KTC/Dezigna | - Share Technical Write-Up - Share costing
64 | Remat Al Riyadh | Surface Public Parking - Phase 3 | Faisal Bin Haddab | LAH | 2025-07-14 | Yes | Strategic bet | Opportunity | 87% |  |  | - Assessing solution with KTC/Dezigna | - Share Technical Write-Up - Share costing
65 | Remat Al Riyadh | Multistorey parking lot 3 - Alamal | Khaled Salem Balobaid | ELW | 2025-07-14 | Yes | Strategic bet | Opportunity | 90.8% |  |  | - Assessing solution with KTC/Dezigna | - Share Technical Write-Up - Share costing
66 | Ministry of Human Resources and Social Development | Operation of Electronic Services for Childcare Centers | Rawan Sultan Alsaadoun | ELW | 2025-07-15 | Yes | Dead weight | Opportunity | 49% |  |  | - Analyzed RFP (not in scope)
67 | Amanat Hail | Traffic Management Solution | Abdulrahman Almarshad | ELW | 2025-07-16 | No | Strategic bet | Lead |  |  |  | - Assigned SPOC for site visit and requirements gathering | - Pending BD to schedule site visit
68 | MOI | Operation and Maintenance Project of the Systems and Programs Center for the Indicators Measurement Center | Khaled Salem Balobaid | ELW | 2025-07-21 | Yes | Dead weight | Failed |  |  |  | - BD dropped this opportunity after sharing it | - BD to share official email on opportunity failure

## Action Tracker
# | Client | Lead Topic | Owner | Action | Action Owner | Date | Status | Comments
5 | Al Haram - Al Madinah | Operation Center- VMS for Operation & Command Center | GHH | DT submitted preliminary costing
|  |  | GHH | Assessed in house capability (not available)
|  |  | GHH | NDA signed with ISS
|  |  | GHH | initiate contact with ISS (rahel) |  | 2025-06-30
6 | The Ministry of Transport and Logistics Services | Highway Inspection & Monitoring Operations | ELW | Sent email to Ahmed Alkhaldi to assign SPOC for exploration |  | 2025-07-22 | Completed
|  |  | ELW | Ahmed Alkhaldi to align with VP and assign SPOC |  | 2025-07-26 | Pending
|  |  | ELW | BD to schedule a site visit |  | 2025-07-26 | Pending
7 | Aseer Municipality | Smart Parking | GHH | MOU signed at LEAP
|  |  | GHH | Shared Survey
|  |  | GHH | Conducted Site Visit
|  |  | GHH | NDA signed with Flowbird
|  |  | GHH | Preliminary parking solution shared
|  |  | GHH | Submit technical write up |  | 2025-07-06 | Completed
|  |  | GHH | Submit costing leveraging vendor |  | 2025-07-06
|  |  | GHH | Pending feedback from Retina | Vendor | 2025-07-10 | Completed
|  |  | GHH | get pricing from AI, because it might be a free POC
|  |  | GHH | High Level Solution Design |  | 2025-07-13 | Completed
|  |  | GHH | Technical Proposal |  | 2025-07-13 | Completed
|  |  | GHH | Get vendors pricings |  |  | Pending
|  |  | GHH | BD to schedule a meeting with Aseer |  |  | Pending
8 | Ministry of Tourism | Hotel Violations | ELW | Attended meeting with client to gather requirements
|  |  | ELW | BD Team to share MOM and detailed requirements
|  |  | ELW | Shared all requirements with AIAT
|  |  | ELW | Received verbal communication: Free POC from Hikvision in 1 week
|  |  | ELW | Draft POC |  | 2025-07-03
|  |  | ELW | Conduct Site visit |  | 2025-07-09
|  |  | ELW | BD to identify new site
9 | SAL Saudi Logistics Services Company SJSC | AI-based logistics solution | LAH | Conducted a site visit |  | 2025-05-22 | Completed
|  |  | LAH | Received site visit report and insights |  |  | Completed
|  |  | LAH | Received CRD from BD |  |  | Completed
|  |  | LAH | Sent an email to Dr. Salem & Aldossary for capability check |  | 2025-06-26 | Completed
|  |  | LAH | Reminder Sent |  | 2025-06-30 | Completed
|  |  | LAH | AI Team: no required capabilities, shared information with BD |  | 2025-07-03 | Completed
|  |  | LAH | Confirm with BD if we can kill it |  | 2025-07-14 | Completed | BD do not want to kill.
|  |  | LAH | BD to share more details (follow up) |  | 2025-07-22
12 | RIPC | Licensing Platform Development | ELW | Drafted QAF |  |  | Completed
|  |  | ELW | Drafted RFI |  |  | Completed
|  |  | ELW | Shared Costing |  |  | Completed
|  |  | ELW | Shared Technical Write-Up |  |  | Completed
|  |  | ELW | Addressed all comments |  |  | Completed
|  |  | ELW | BD to submit proposal - pending board approval |  | 2025-06-23 | In Progress
13 | Civil Defense | Fire & Safety IOT [N/A] | GHH | Initiate installation in KAFD |  |  | Completed | waiting for Faisal to come back from vacation and tell him to send email to AI
|  |  | GHH | Pending NDA between KAFD and Honeywell |  |  | In Progress
|  |  | GHH | AIAT allocate a SPOC for the project exploration
|  |  | GHH | Finalizing NDA |  |  | In Progress
20 | Saudi Aramco | Urban Eye: Visual Pollution Project | ELW | Aligned with DT team on environments readiness and costing |  |  | Completed | There is another thread between BD and AI, we're not included in it, they are aligning and pending client approval that they need poc to share it
|  |  | ELW | Shared insights from site visit |  |  | Completed
|  |  | ELW | Ahmad alkhaldi to provide poc costing structure with DT putting in mind duration is 1 month
|  |  | ELW | DT shared technical write-up and costing |  |  | Completed
|  |  | ELW | Abdulaziz Almuhsen shared POC |  |  | Completed
|  |  | ELW | POC Report shared with Aramco |  |  | Completed
|  |  | ELW | Pending client to provide feedback and update on next steps |  |  | In Progress
21 | KFCA | Urban Mobility Solutions [AI-Driven Traffic Management] | ELW | Provided list of required qualification documents |  |  | Completed
|  |  | ELW | QAF scored 80%
|  |  | ELW | Received RFP |  | 2025-07-01 | Completed
|  |  | ELW | Share Questions |  | 2025-07-08 | Completed
|  |  | ELW | High Level Solution Design |  | 2025-07-17
|  |  | ELW | Estimated Cost |  | 2025-07-20
|  |  | ELW | Technical Proposal |  | 2025-07-31
|  |  | GHH | GHH to align with AZZ about AI situation |  | 2025-07-28
22 | Al Haram - Al Madinah | Holy Mosque Courtyard | LAH | POC document/solution was provided (by AI Team)
|  |  | LAH | Cost estimate was provided
|  |  | LAH | Reminders sent to BD
|  |  | LAH | Sent reminder 2 - BD SPOC to provide answer regarding 12 months execution |  | 2025-06-19 | Completed
|  |  | LAH | Reminder 3 sent - BD SPOC to provide answer regarding 12 months execution |  | 2025-07-08 | Completed
|  |  | LAH | Received confirmation that presales team agreed to proceed with the 12 months execution |  | 2025-07-23 | Completed
|  |  | LAH | Sent email to Aldossari to provide us with the requirements and assumptions |  | 2025-07-22 | Completed
|  |  | LAH | Abdullah Aldossari to provide us with the requirmeents and assumptions as requested by Ahmed Alraba |  | 2025-07-24 | Completed
|  |  | LAH | AI team to provide detailed timeline (12months) |  | 2025-07-27 | Completed
45 | RIPC | Development of Monitoring Platform | ELW | Shared QAF |  |  | Completed
|  |  | ELW | Shared RFI |  |  | Completed
|  |  | ELW | Shared Costing |  |  | Completed
|  |  | ELW | Shared Technical Write-Up |  |  | Completed
|  |  | ELW | Addressed all comments |  |  | Completed
|  |  | ELW | BD to provide stauts - waiting approval |  |  | In Progress
46 | MOI-Transformation Program | Multiple opportunities received for evaluation | GHH | Shared the excel with BD |  |  | Completed
|  |  | GHH | Follow up with BD on next steps |  | 2025-07-28
|  |  | GHH | Attend meeting with BD + Client | ELW
48 | Amanat Alsharqiyah | Smart Parking | ELW | Drafted Solution |  |  |  | Aseel Almoosa is the Account Manager, reached out to her on June 16 to get an update, client still asessing
|  |  | ELW | Follow up with business to understand the next steps
51 | National Center for Privatization & PPP | Driving School | ELW | BD team conducted initial understanding meeting with the client |  |  | Completed
|  |  | ELW | BD team shared RFP |  |  | Completed
|  |  | ELW | To attend kickoff meeting with EDC (Partner) |  |  | Completed
|  |  | ELW | Share questions |  | 2025-07-06 | Completed
|  |  | ELW | Share cost |  | 2025-07-31
|  |  | ELW | Share Write-Up |  | 2025-08-10
|  |  | ELW | Alkhaldi to formulate a technical team
52 | Remat Al Riyadh | Surface Public Parking Project – Phase One | LAH | Shared QAF |  |  | Completed
|  |  | LAH | Questionnaire |  | 2025-06-26 | Completed
|  |  | LAH | Technical Write-up + Cost |  | 2025-07-06 | On-Hold
53 | Remat Al Riyadh | Surface Public Parking Project – Phase Two | LAH | Shared QAF
|  |  | LAH | Questionnaire |  | 2025-06-26 | Completed
|  |  | LAH | Technical Write-up + Cost |  | 2025-07-06 | On-Hold
54 | Remat Al Riyadh | Multistorey Parking Project – Al Sahafa District | ELW | Drafted Opportunity Card
|  |  | ELW | Shared QAF
|  |  | ELW | Shared Questionnaire |  | 2025-07-09 | Completed
|  |  | ELW | Technical Write-up + Cost |  | 2025-08-01
56 | MWAN | Construction Waste Solution | LAH | Sent an email to Dr. Salem & Aldossary for capability check |  | 2025-06-30 | Completed
|  |  | LAH | Shared AI's confirmation regarding available capabilities with BD |  |  | Completed
|  |  | LAH | Sent follow up on lead status |  | 2025-07-08 | Completed
|  |  | LAH | Send reminder |  | 2025-07-17 | Completed
|  |  | LAH | Pending BD update |  | 2025-07-17 | Completed
|  |  | LAH | Abdulaziz Almuhsen to share availibilty to discuss POC with client |  | 2025-07-21 | Completed
|  |  | LAH | BD to set a meeting with client to discuss POC req. |  | 2025-07-27
57 | Riyadh Airport | Visual Pollution | LAH | Sent an email to Dr. Salem & Aldossary for capability check () |  | 2025-06-26 | Completed
|  |  | LAH | Shared AI's confirmation regarding available capabilities with BD |  |  | Completed
|  |  | LAH | Sent follow up on lead status |  | 2025-07-08 | Completed
|  |  | LAH | AI Suggested POC - Requested from AI Team information to proceed with POC |  | 2025-07-09 | Completed
|  |  | LAH | Reminder to AI if no answer |  | 2025-07-14 | Completed
|  |  | LAH | Confirmed to BD POC cost & timeline |  | 2025-07-14 | Completed
|  |  | LAH | Request from AI hardware + Cost |  | 2025-07-17 | Completed
|  |  | LAH | Share hardware cost with Abdualziz alshadayed |  | 2025-07-27 |  | Pending Abdualziz Almohsen
58 | Civil Defense | List of 26 opportunities | GHH | Attended meeting with Civil Defense to align on the priorities |  |  | Pending | To be discussed with AZZ
|  |  | GHH | Prioritize opportunities and secure approval from management on next steps |  |  | Pending
59 | Ministry of Tourism | Hotel Evaluation Criteria | LAH | Requested requirements/RFP from Muath to assist in BD QAF |  | 2025-07-14 | Completed
|  |  | LAH | Get back to Muath with AIAT QAF |  | 2025-07-21 | Pending | pending Requirements/RFP receipt
|  |  | LAH | Sent email to AI team to check if we have the capability or not |  | 2025-07-24 | Pending | pending ai team response
60 | GSTC | Performance Management Solution | LAH | BD requested capability confirmation - scope was not clear - asked for RFP |  | 2025-07-07 | Completed
|  |  | LAH | Rawan/Danah to set up meeting with client |  |  | Pending
61 | Remat Al Riyadh | Surface Public Parking Project – Murabah Street | LAH | Prepare QAF |  | 2025-07-16 | Completed
|  |  | LAH | Prepare Questionnaire |  | 2025-07-20 | Completed
|  |  | LAH | Prepare Tecnical Write-up + Cost |  | 2025-07-28
62 | Remat Al Riyadh | Mechanical Parking - Lot 4 | LAH | Prepare QAF |  | 2025-07-16 | Completed
|  |  | LAH | Prepare Questionnaire |  | 2025-07-20 | Completed
|  |  | LAH | Prepare Estimated Cost |  | 2025-07-29
|  |  | LAH | Prepare Tecnical Write-up |  | 2025-08-03
|  |  | LAH | Prepare final cost |  | 2025-08-07
63 | Remat Al Riyadh | Multistorey parking - Lot 5 | ELW | Prepare QAF |  | 2025-07-15 | Completed
|  |  | ELW | Prepare Questionnaire |  | 2025-07-30
|  |  | ELW | Prepare technical Write-up + Cost |  | 2025-08-10
64 | Remat Al Riyadh | Surface Public Parking - Phase 3 | LAH | Prepare QAF |  | 2025-07-16 | Completed
|  |  | LAH | Prepare Questionnaire |  | 2025-07-23 | Completed | Questionnaire ready in shared folder - to send on the 23rd
|  |  | LAH | Prepare technical Write-up + Cost |  | 2025-08-10
65 | Remat Al Riyadh | Multistorey parking lot 3 - Alamal | ELW | Prepare QAF |  | 2025-07-15 | Completed
|  |  | ELW | Prepare Questionnaire |  | 2025-07-30
|  |  | ELW | Prepare technical Write-up + Cost |  | 2025-08-10
66 | Ministry of Human Resources and Social Development | Operation of Electronic Services for Childcare Centers | ELW | Prepare QAF |  | 2025-07-17 | Completed
|  |  | ELW | Prepare Questionnaire |  |  | On-Hold
|  |  | ELW | Prepare technical Write-up + Cost |  |  | On-Hold
67 | Amanat Hail | Traffic Management Solution | GHH | BD Requested SPOC from AIAT for field visit |  | 2025-07-16 | Completed
|  |  | ELW | AIAT to allocate SPOC |  | 2025-07-17 | Completed
|  |  | ELW | Waiting for BD site visit report |  | 2025-07-27
|  | Fleet Management | GHH | Fleet Management |  | 2025-07-28

## Internal Pipeline
# | Client | Lead Topic | SPOC | LEAD | Received | RFP | Category | Status | QAF | Submission Deadline | Vendor needed? | Actions done | Next Step | Deadline for Next Step | Comments | MSR | Actions Done (Only to be added to BD case)
1 | Haramen |  | Ghazi | RAE
2 | MOMAH |  | Hassan Alassiri | RAE
3 | MOI |  | Abdallah zaki | RAE

## Access
Username | Password
ELW | FourPrinciples2025
GHH | FourPrinciples2025
RAE | FourPrinciples2026
AZZ | Tahakom2025
aalghobaish | Tahakom2025

## Settings
Client | RFP | Category | Status | BD SPOC | FP LEAD | MSR
Al Haram - Al Madinah | Yes | Dead weight | Failed | Muath Fahad Almohawes | ELW | 1
Al Haram - Al Madinah - Operation Center | No | Hot deals | Lead | Mohammad Abdulkarim​​​​ Almuhesseny | LAH | 2
Aseer Municipality | RFI | Strategic bet | Opp-Lost | Faisal Bin Haddab | GHH | 3
Civil Defense |  | Tactical distraction | Opp-OnHold | Abdulaziz Mohammed​​​​ Alshedayed | RAE | 4
DGA |  |  | Opportunity | Danah Alothman |  | 5
GCA |  |  | Opp-Submitted | Abdullah Almehrej |  | 6
Great Amman Municipality |  |  | Opp-Win | Abdulrahman Almarshad
Haramen |  |  | POC | Saleh Alfuzan
Jeddah Municipality |  |  | TBD | Omar Hatem S Aldossary
KFCA |  |  | FP Lead | Khaled Salem Balobaid
Ministry of National Guard Development |  |  | Line cancelled | Abdulaziz Alshedayed
Ministry of Tourism |  |  |  | Abdulaziz Alkhwatiem
MOF |  |  |  | Mohammed Abdulrahman​​​​ Alyabis
MOI |  |  |  | Ahmed Mohamad A Alraba
MOI-Transformation Program |  |  |  | Rawan Sultan Alsaadoun
MOJ |  |  |  | Mohammad Abdullah M Alwateed
MOMAH |  |  |  | GHH
National Observatory for Quality of Life |  |  |  | ELW
RCRC |  |  |  | LAH
Remat Al Riyadh |  |  |  | Vendor
RIPC
Riyadh Municipality |  |  |  | N/A
SAL Saudi Logistics Services Company SJSC
SAR
Saudi Aramco
The Ministry of Transport and Logistics Services
Trust Fund Minors And Their Counterparts
COOP/Tawuniya driving
Amanat Alsharqiyah
SWA
National Center for Privatization & PPP
State Properties General Authority - SPGA
MWAN
Riyadh Airport
Ministry of Human Resources and Social Development
GSTC
Amanat Hail